## Cloud Risk Register
ID | Asset | Risk Description | Likelihood | Impact | Risk Score | Control | Owner | Status
CR-01 | S3 Buckets | Misconfigured public access leads to data breach | High | High | 25 | Block Public Access + IAM Policy | CISO | Open
CR-02 | IAM Roles | Excessive permissions (Privilege Escalation) | Medium | High | 20 | Least Privilege + SCP | Cloud Security Team | In Progress
CR-03 | CloudTrail Logs | Logs disabled or deleted | Medium | Medium | 16 | Enable CloudTrail + S3 versioning | GRC Analyst | Open
CR-04 | RDS Database | Unencrypted storage or snapshots | Medium | High | 20 | KMS Encryption + IAM Access Controls | DevOps | In Progress
CR-05 | AWS Console Access | No MFA for admin accounts | High | High | 25 | MFA Enforcement | CISO | Closed